## Gantt_Excel_Pro_Hourly_nhom5
Create professional Gantt charts in GanttPRO in a few clicks
Gantt_Excel_Pro_Hourly_nhom5 | [10 empty] | 2022-05-27 16:47
Color | WBS Number |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Predecessor | Resourse | Created | Creator | Type | Project | Level
| 1 | 1.1 Bắt đầu |  |  | 2022-04-18 09:00 | 2022-04-22 18:00 |  | 100 | 40 | 0 | 0 | [5 empty] | 2022-05-27 22:35 |  | project | Gantt_Excel_Pro_Hourly_nhom5 | 1
| 1.1 |  | 1.1.1 Đánh giá & Khuyến nghị |  | 2022-04-18 09:00 | 2022-04-18 18:00 |  | 100 | 8 | 0 | 0 | Done | Medium |  |  | Nguyễn Cương, Hoàng Đức, Nguyễn Thúy, Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.1 Bắt đầu | 2
| 1.2 |  | 1.1.2 Phát triển các điều lệ dự án |  | 2022-04-19 09:00 | 2022-04-21 13:00 |  | 100 | 20 | 0 | 0 | Done | Medium |  | 1.1 | Nguyễn Thúy | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.1 Bắt đầu | 2
| 1.3 |  | 1.1.3 Phát triển các trường hợp kinh doanh |  | 2022-04-19 09:00 | 2022-04-21 13:00 |  | 100 | 20 | 0 | 0 | Done | Medium |  | 1.1 | Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.1 Bắt đầu | 2
| 1.4 |  | 1.1.4 Có thể giao: Gửi Điều lệ Dự án, Gửi trường hợp kinh doanh |  | 2022-04-21 14:00 | 2022-04-21 18:00 |  | 100 | 4 | 0 | 0 | Done | Medium |  | 1.3 | Hoàng Đức | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.1 Bắt đầu | 2
| 1.5 |  | 1.1.5 Nhà tài trợ dự án Đánh giá Điều lệ dự án và trường hợp kinh doanh |  | 2022-04-22 09:00 | 2022-04-22 13:00 |  | 100 | 4 | 0 | 0 | Done | Medium |  | 1.4 | Nguyễn Cương | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.1 Bắt đầu | 2
| 1.6 |  | 1.1.6 Điều lệ dự án Đã ký / Phê duyệt |  | 2022-04-22 14:00 | 2022-04-22 18:00 |  | 100 | 4 | 0 | 0 | Done | Medium |  | 1.5 | Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.1 Bắt đầu | 2
| 2 | 1.2 Lập kế hoạch |  |  | 2022-04-25 09:00 | 2022-05-06 18:00 |  | 100 | 80 | 0 | 0 | [5 empty] | 2022-05-27 22:35 |  | project | Gantt_Excel_Pro_Hourly_nhom5 | 1
| 2.1 |  | 1.2.1 Tạo Tuyên bố Phạm vi Sơ bộ |  | 2022-04-25 09:00 | 2022-04-25 18:00 |  | 100 | 8 | 0 | 0 | Done | Medium |  | 1.6 | Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.2 Lập kế hoạch | 2
| 2.2 |  | 1.2.2 Xác định nhóm dự án |  | 2022-04-26 09:00 | 2022-04-27 18:00 |  | 100 | 16 | 0 | 0 | Done | Medium |  | 2.1 | Nguyễn Thúy | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.2 Lập kế hoạch | 2
| 2.3 |  | 1.2.3 Họp khởi động nhóm dự án |  | 2022-04-28 09:00 | 2022-04-28 12:00 |  | 100 | 3 | 0 | 0 | Done | Medium |  | 2.2 | Nguyễn Cương | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.2 Lập kế hoạch | 2
| 2.4 |  | 1.2.4 Phát triển kế hoạch dự án |  | 2022-04-28 12:00 | 2022-05-05 17:00 |  | 100 | 44 | 0 | 0 | Done | Medium |  | 2.3 | Nguyễn Cương, Hoàng Đức, Nguyễn Thúy, Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.2 Lập kế hoạch | 2
| 2.5 |  | 1.2.5 Gửi kế hoạch dự án |  | 2022-05-05 17:00 | 2022-05-06 10:00 |  | 100 | 2 | 0 | 0 | Done | Medium |  | 2.4 | Hoàng Đức | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.2 Lập kế hoạch | 2
| 2.6 |  | 1.2.6 Mốc quan trọng: Phê duyệt kế hoạch dự án |  | 2022-05-06 10:00 | 2022-05-06 18:00 |  | 100 | 7 | 0 | 0 | Done | Medium |  | 2.5 | Nguyễn Thúy, Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.2 Lập kế hoạch | 2
| 3 | 1.3 Thực thi |  |  | 2022-05-09 09:00 | 2022-05-27 18:00 |  | 93 | 120 | 0 | 0 | [5 empty] | 2022-05-27 22:35 |  | project | Gantt_Excel_Pro_Hourly_nhom5 | 1
| 3.1 |  | 1.3.1 Cuộc họp khởi động dự án |  | 2022-05-09 09:00 | 2022-05-09 13:00 |  | 100 | 4 | 0 | 0 | Done | Medium |  | 2.6 | Nguyễn Cương, Hoàng Đức, Nguyễn Thúy, Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.3 Thực thi | 2
| 3.2 |  | 1.3.2 Xác minh & xác thực các yêu cầu của người dùng |  | 2022-05-09 14:00 | 2022-05-12 18:00 |  | 100 | 28 | 0 | 0 | Done | Medium |  | 3.1 | Nguyễn Thúy, Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.3 Thực thi | 2
| 3.3 |  | 1.3.3 Thiết kế hệ thống |  | 2022-05-13 09:00 | 2022-05-19 18:00 |  | 100 | 40 | 0 | 0 | Done | Medium |  | 3.2 | Nguyễn Cương, Hoàng Đức, Nguyễn Thúy, Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.3 Thực thi | 2
| 3.4 |  | 1.3.4 Mua sắm phần cứng / phần mềm |  | 2022-05-20 09:00 | 2022-05-20 18:00 |  | 100 | 8 | 0 | 0 | Done | Medium |  | 3.3 | Hoàng Đức | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.3 Thực thi | 2
| 3.5 |  | 1.3.5 Cài đặt hệ thống phát triển |  | 2022-05-23 09:00 | 2022-05-23 13:00 |  | 100 | 4 | 0 | 0 | Done | Medium |  | 3.4 | Nguyễn Cương, Hoàng Đức | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.3 Thực thi | 2
| 3.6 |  | 1.3.6 Giai đoạn thử nghiệm |  | 2022-05-23 14:00 | 2022-05-24 17:00 |  | 86 | 11 | 0 | 0 | In progress | Medium |  | 3.5 | Hoàng Đức, Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.3 Thực thi | 2
| 3.7 |  | 1.3.7 Cài đặt hệ thống trực tiếp |  | 2022-05-24 17:00 | 2022-05-25 12:00 |  | 88 | 4 | 0 | 0 | In progress | Medium |  | 3.6 | Nguyễn Cương, Nguyễn Thúy | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.3 Thực thi | 2
| 3.8 |  | 1.3.8 Đào tạo người dùng |  | 2022-05-25 12:00 | 2022-05-27 13:00 |  | 88 | 17 | 0 | 0 | In progress | Medium |  | 3.7 | Nguyễn Thúy | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.3 Thực thi | 2
| 3.9 |  | 1.3.9 Cài đặt |  | 2022-05-27 14:00 | 2022-05-27 18:00 |  | 0 | 4 | 0 | 0 | Open | Medium |  | 3.8 |  | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.3 Thực thi | 2
| 4 | 1.4 Kiểm thử phần mềm |  |  | 2022-05-30 09:00 | 2022-06-03 13:00 |  | 74 | 36 | 0 | 0 | [5 empty] | 2022-05-27 22:35 |  | project | Gantt_Excel_Pro_Hourly_nhom5 | 1
| 4.1 |  | 1.4.1 Kiểm thử hệ thống |  | 2022-05-30 09:00 | 2022-05-31 18:00 |  | 83 | 16 | 0 | 0 | In progress | Medium |  | 3.9 | Nguyễn Cương, Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.4 Kiểm thử phần mềm | 2
| 4.2 |  | 1.4.2 Kiểm thử đơn vị |  | 2022-06-01 09:00 | 2022-06-02 13:00 |  | 78 | 12 | 0 | 0 | In progress | Medium |  | 4.1 | Hoàng Đức, Nguyễn Thúy | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.4 Kiểm thử phần mềm | 2
| 4.3 |  | 1.4.3 Kiểm thử chấp nhận người dùng |  | 2022-06-02 14:00 | 2022-06-03 13:00 |  | 50 | 8 | 0 | 0 | In progress | Medium |  | 4.2 | Hoàng Đức, Nguyễn Thúy | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / 1.4 Kiểm thử phần mềm | 2
| 5 | Kết thúc |  |  | 2022-06-03 14:00 | 2022-06-06 15:00 |  | 0 | 9 | 0 | 0 | [5 empty] | 2022-05-27 22:35 |  | project | Gantt_Excel_Pro_Hourly_nhom5 | 1
| 5.1 |  | 1.5.1 Cập nhật tệp / hồ sơ |  | 2022-06-03 14:00 | 2022-06-03 16:00 |  | 0 | 2 | 0 | 0 | Open | Medium |  | 4.3 | Nguyễn Thúy, Lê Linh | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / Kết thúc | 2
| 5.2 |  | 1.5.2 Đạt được sự chấp nhận chính thức |  | 2022-06-03 16:00 | 2022-06-06 11:00 |  | 0 | 4 | 0 | 0 | Open | Medium |  | 5.1 | Hoàng Đức | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / Kết thúc | 2
| 5.3 |  | 1.5.3 Lưu trữ Tệp / Tài liệu |  | 2022-06-06 11:00 | 2022-06-06 15:00 |  | 0 | 3 | 0 | 0 | Open | Medium |  | 5.2 | Nguyễn Cương | 2022-05-27 22:35 |  | task | Gantt_Excel_Pro_Hourly_nhom5 / Kết thúc | 2
This document has been created with the help of https://ganttpro.com online service